## Read Me
UBUNTU LAND TRUST & DEVELOPMENTS · Common Ground Initiative
1279 Simcoe Street North — Read Me
Formula-driven Common Ground model — September 2026 handoff
What this is | An editable, formula-driven model of the 1,000-home R01 concept at 1279 Simcoe Street North, Oshawa, structured under the Ubuntu Land Trust Common Ground Initiative (land lease, CMHC MLI Select 50% / Build Canada Homes 40% split tranche / City 5% / landowner retained equity 5%; 30% of homes at 80% of CMHC median market rent). It answers the September 2026 handoff: test the $17M ask, solve supportable land value, compare density and timing alternatives, identify peak funding exposure.
Status | PRELIMINARY SCENARIO BRIEF. The 1,000-home scheme is an unapproved capacity concept. Nothing here is a valuation, appraisal, offer or lender commitment.
Colour code | Yellow cells = editable inputs (Inputs tab). Red cells = PLACEHOLDER / UNVERIFIED / PENDING inputs that must be replaced before reliance. Lilac cells = values computed by the companion engine (model/cg_engine.py) because they need goal-seek or data-table behaviour; re-run build_workbook.py after changing inputs to refresh them. Everything else is a live formula.
Under Common Ground the land is not bought | The landowner receives a Day-1 draw (60% of appraisal) at each phase's financial close, keeps retained equity equal to 5% of that phase's total development cost, takes 60% of net cash flow after MLI Select debt service for the phase's Years 1-10, and is bought out at Year 10 (retained equity + MLI principal paid down) through a 50-year supplemental charge. Appraisal above draw + equity is value donated to affordability. BCH takes the 60% seat in Years 11-20 to sweep its mezzanine. The 'purchase price' in the handoff is therefore tested as the APPRAISAL that drives the draw, and 'supportable land value' is the largest appraisal at which every Common Ground test passes.
Common Ground feasibility tests | 1) Consolidated lender DSCR at stabilization ≥ min_dscr (NOI after replacement reserve ÷ MLI debt service). 2) Each phase's Year-10 DSCR incl. the supplemental charge ≥ 1.10. 3) Non-profit annual net cash flow ≥ 0 in every phase-year after stabilization (lease-up deficits are funded from the capitalized reserve). 4) Year-20 takeout: refinance at takeout_ltv × value clears MLI + supplemental + mezz balances.
Conventions | Monthly periods; month 1 = t_start (Inputs). Nominal dollars; growth rates on Inputs. Rents step annually from each phase's completion. Stabilized NOI = the 12 months after the month occupancy first reaches stab_occ. Valuation NOI excludes the replacement reserve; lender DSCR NOI deducts it. Phase 1 pays front-loaded site/remediation works (infra_p1_share). Sources = uses each month: City → BCH contribution → BCH mezz → MLI Select, in that order; MLI construction interest is capitalized. Before income tax; land transfer tax off by default (land lease); HST net cost is a PENDING input.
Hurdles | The handoff asks the investment team to select target IRR, minimum margin and hold period. Until supplied, the Exit & Residual tab shows several explicitly labelled hurdles (target_yoc, target_margin, disc_rate on Inputs) rather than a house standard.
Tabs | Sources · Inputs · Programme · Schedule · Development Budget · Revenue & Opex · Debt · Monthly Cash Flow · Phase Returns · Exit & Residual · Sensitivities · Dashboard · Checks
Companion files | model/cg_engine.py (engine + input register), model/build_workbook.py (this builder), 1279_Simcoe_FINDINGS_MEMO.html, 1279_Simcoe_SOURCE_REGISTER.md

## Sources
UBUNTU LAND TRUST & DEVELOPMENTS · Common Ground Initiative
1279 Simcoe Street North — Source register
Where every external input came from, what was reachable, and what remains PENDING
# | Source | What it supplied | Date | Reached? | Confidence | Used for
1 | City of Oshawa, Economic & Development Services — Item ED-24-20, Attachment 2, Proposed Draft Plan of Subdivision, 1279 Simcoe St N (Katanna Simcoe Ltd.), files S-O-2022-05 / Z-2022-12 / C-O-2022-08 | Block 1 = 3.1211 ha, 172 condo townhouses (traditional, back-to-back, live-work); Block 2 road widening 5.5 m × 87.4 m; assembly of PINs 16285-0006/-0009/-0153/-0151; Lot 27 (PIN 16285-0008) and Lot 24 excluded | Jan 2024 | Yes (uploaded PDF) | H | site_net_m2; approved-plan cross-check
2 | Financial Modelling Handoff (internal), 15 Sep 2026 | R01 programme (86,208 m² above ground, 83,408 m² residential gross, 2,800 m² other, 650 spaces, 20,800 m² below grade), suite mix, $17M ask, 7.85 ac, ~$500k existing NOI, 170-unit / 313,966 sf townhouse benchmark, $102,653/home DC placeholder, 0.9823% tax rate, $290-390/sf benchmark | 2026-09-15 | Yes | M (measured) / L (commercial) | Programme; land_appraisal; dc_per_home; scenario framework
3 | Arterial — resolve_site | Parcel 17,014 m² (ONE PIN of the assembly, 72.8 m × 276.6 m), 5 existing buildings 6,070 m² footprint, Regional Road 2 (Simcoe St N, 5 lanes) | 2026-09-15 | Yes | M | exist_footprint; site note
4 | Arterial — financial_context (constructionCost) | Condos up to 12 storeys $290-390/sf (dataset 8fd5356d); 3-storey stacked townhouse $230-270/sf | 2026-09-15 | Yes | L (scope not inspected) | hard_psf; townhouse cross-check
5 | Arterial — financial_context (propertyTax) | 0.9823% multi-residential, Oshawa 2025 | 2026-09-15 | Yes | L (unverified) | tax_rate
6 | Arterial — financial_context (developmentCharges, cmhcRents) | NO Oshawa development-charge dataset; CMHC zone 'Oshawa (North)' returned no rent values | 2026-09-15 | Yes (empty) | — | DC and MMR remain placeholders
7 | Arterial — run_development_scenario (Optimal Townhouse, 172 units, rental) | 3-BR comps avg $2,412 (4 comps; 53 Taunton Rd E $2,400-2,450 at ~1,100-1,300 sf; 97 Nonquon Rd $2,399); 1-BR $1,795 (1 comp); 2-BR $2,173 (2 comps); residual land value NEGATIVE as rental | 2026-09-15 | Yes | L | rent_1/2/3; comp sizes
8 | Arterial — find_unit_comps (sales, condo townhouse, Centennial) | 8 active listings Jun-Jul 2026: 3-BR ~1,100 sf $430k-475k (~$411/sf), 2-BR ~950 sf $330k-399k (~$388/sf); 50-year-old stock | 2026-09-15 | Yes | L (asking, not closed) | Townhouse for-sale cross-check
9 | Arterial — run_hbu_development_scenario | Job started three times; result never returned within the session ('computing') and the result URL is blocked from this environment | 2026-09-15 | No | — | Not used
10 | Arterial — analyze_zoning (via scenario policy context) | 'No policy text or zoning data covering this parcel was found' — Oshawa By-law 60-94 not in Arterial | 2026-09-15 | Yes (empty) | — | Entitlement treated as rezoning required
11 | CMHC Rental Market Survey, Oshawa CMA, Oct 2025 (HMIP portal) | Median market rents by bedroom | 2025-10 | NO — domain blocked from this session | — | mmr_0..3 are PENDING placeholders
12 | City of Oshawa development charges page / By-law 104-2025; Region of Durham DC page; DRHBA updates | Current per-unit DC schedule (City, Region, education) | 2025 | NO — domains blocked from this session | — | dc_per_home stays at supplied placeholder
13 | Durham Post, 'Oshawa council to consider 172-unit townhouse project'; Oshawa council information memo (escribe DocumentId 14949) | Approval status of Z-2022-12 / S-O-2022-05 | 2024 | NO — domains blocked; search snippet only | — | Approval status UNCONFIRMED
14 | Platinum Condo Deals / LoopNet / Zolo listings for 1279 Simcoe St N | Marketing now shows 165 units in 20 blocks (Katanna Developments); commercial units D/F/G for lease at the existing plaza | 2026 | Search snippets only | L | Existing-use note; unit-count revision
15 | Ubuntu Common Ground skill (July 2026 structure) — generate_package.py | Capital stack, splits, Day-1 draw, Year-10 buyout, Year-20 takeout, opex defaults, cap/mortgage/vacancy defaults | 2026-07 | Yes | H (programme rules) | All Common Ground mechanics

## Inputs
UBUNTU LAND TRUST & DEVELOPMENTS · Common Ground Initiative
1279 Simcoe Street North — Inputs & assumption register
Yellow = editable · Red = placeholder/unverified/pending · every input carries source, date, units, confidence, owner
Group | Key | Value | Unit | Label | Source / basis | Date | Conf. | Owner | Flag
Site & acquisition
Site & acquisition | site_net_m2 | 31211 | m² | Net site (R01 Block 1) | Draft plan S-O-2022-05, Attachment 2 to ED-24-20 (3.1211 ha) | 2024-01 | H | Survey
Site & acquisition | site_gross_ac | 7.85 | acres | Gross site per acquisition summary | Supplied acquisition summary; reconcile to survey | 2026-09 | L | Vendor | UNVERIFIED
Site & acquisition | land_appraisal | 17000000 | $ | Land value used for Common Ground draw (seller ask as placeholder) | Seller ask $17.0M; NOT an appraisal. Common Ground requires an AACI appraisal | 2026-09 | L | Vendor | PLACEHOLDER
Site & acquisition | draw_pct | 60% | % | Day-1 landowner draw as % of appraisal | Common Ground July 2026 structure (locked) | 2026-07 | H | Ubuntu
Site & acquisition | land_eq_pct | 5% | % of TDC | Landowner retained equity | Common Ground July 2026 structure (locked) | 2026-07 | H | Ubuntu
Site & acquisition | draw_timing | 1 | 1 = pro rata by phase homes; 0 = 100% at Phase 1 close | Land draw timing | Analyst assumption; editable | 2026-09 | M | Analyst
Site & acquisition | existing_noi | 500000 | $/yr | Existing NOI (seller-supplied) | Vendor summary; rent roll, leases and expenses NOT provided | 2026-09 | L | Vendor | UNVERIFIED
Site & acquisition | existing_noi_keep | 0% | share | Share of existing NOI retained during entitlement (0 = zero-retained-income case) | Handoff §2: use zero-retained case unless leases support retention | 2026-09 | M | Analyst
Site & acquisition | legal_title | 150000 | $ | Legal, title, lease registration, due diligence | Analyst placeholder | 2026-09 | L | Analyst | PLACEHOLDER
Site & acquisition | ltt_applies | 0 | 1/0 | Land transfers to SPV (Ontario LTT applies)? | Common Ground = land lease, no transfer; set 1 if structure changes | 2026-09 | M | Ubuntu
Site & acquisition | carry_taxes | 120000 | $/yr | Property tax + insurance on existing site during entitlement | Analyst placeholder pending tax bill | 2026-09 | L | Analyst | PLACEHOLDER
Schedule
Schedule | t_start | 2027-01-01 | date | Month 1 (financial close / lease commencement) | Analyst assumption; editable | 2026-09 | M | Analyst
Schedule | entitle_months | 18 | months | Entitlement (OPA/ZBA + SPA) before Phase 1 construction | Analyst assumption; planner input required | 2026-09 | L | Planner | PLACEHOLDER
Schedule | entitle_delay | 0 | months | Approval delay stress (added to entitlement) | Scenario lever | 2026-09 | H | Analyst
Schedule | constr_m_8 | 26 | months | Construction duration, 8-storey building | Analyst assumption; no schedule established (handoff §3) | 2026-09 | L | Analyst | PLACEHOLDER
Schedule | constr_m_12 | 30 | months | Construction duration, 12-storey building | Analyst assumption; no schedule established (handoff §3) | 2026-09 | L | Analyst | PLACEHOLDER
Schedule | seq_mode | 1 | 1 = sequential; 0 = overlap by interval | Phase sequencing | Handoff §6: sequential reference case | 2026-09 | H | Analyst
Schedule | overlap_interval | 12 | months | Start interval between phases when overlapping | Scenario lever | 2026-09 | H | Analyst
Schedule | later_defer | 0 | months | Defer Phases 2-4 (stress) | Scenario lever | 2026-09 | H | Analyst
Schedule | lease_cap | 25 | homes/month | Sitewide leasing capacity (all phases compete) | Analyst assumption; no absorption evidence supplied | 2026-09 | L | Analyst | PLACEHOLDER
Schedule | lease_cap_mult | 1 | × | Leasing pace multiplier (stress) | Scenario lever | 2026-09 | H | Analyst
Schedule | retail_delay | 6 | months | Retail lease-up delay after phase completion | Analyst placeholder | 2026-09 | L | Analyst | PLACEHOLDER
Schedule | hold_after_stab | 120 | months | Operating hold after final stabilization | Handoff §1 | 2026-09 | H | Client
Rents (market)
Rents (market) | rent_0 | 1495 | $/mo | Studio market rent | NO COMP SUPPLIED. Analyst placeholder from 1-BR $/sf scaled; verify new-build achieved rents | 2026-09 | L | Analyst | PLACEHOLDER
Rents (market) | rent_1 | 1795 | $/mo | 1-bedroom market rent | Arterial leasing comps, 1 comp (650 sf resale condo, Centennial) | 2026-09 | L | Arterial | UNVERIFIED
Rents (market) | rent_2 | 2173 | $/mo | 2-bedroom market rent | Arterial leasing comps, 2 comps (avg 1,025 sf resale condo/townhouse) | 2026-09 | L | Arterial | UNVERIFIED
Rents (market) | rent_3 | 2412 | $/mo | 3-bedroom market rent | Arterial leasing comps, 4 comps (avg 1,300 sf, e.g. 53 Taunton Rd E $2,400-2,450) | 2026-09 | L | Arterial | UNVERIFIED
Rents (market) | newbuild_prem | 0% | % | New-build rent premium over comps | Handoff §1: do not assume a premium | 2026-09 | H | Analyst
Rents (market) | rent_shock | 0% | % | Starting-rent stress (±) | Scenario lever | 2026-09 | H | Analyst
Rents (market) | comp_sf_1 | 650 | sf | Comp reference size 1-BR | Arterial comps | 2026-09 | M | Arterial
Rents (market) | comp_sf_2 | 1025 | sf | Comp reference size 2-BR | Arterial comps | 2026-09 | M | Arterial
Rents (market) | comp_sf_3 | 1300 | sf | Comp reference size 3-BR | Arterial comps | 2026-09 | M | Arterial
Rents (affordable / CMHC)
Rents (affordable / CMHC) | mmr_0 | 1250 | $/mo | CMHC median market rent, bachelor (Oshawa CMA) | PENDING — CMHC Rental Market Survey Oct 2025 (HMIP portal not reachable from this session); Arterial CMHC zone 'Oshawa (North)' returned no value | 2025-10 | L | CMHC | PENDING
Rents (affordable / CMHC) | mmr_1 | 1500 | $/mo | CMHC median market rent, 1-bedroom | PENDING — as above | 2025-10 | L | CMHC | PENDING
Rents (affordable / CMHC) | mmr_2 | 1750 | $/mo | CMHC median market rent, 2-bedroom | PENDING — as above | 2025-10 | L | CMHC | PENDING
Rents (affordable / CMHC) | mmr_3 | 1950 | $/mo | CMHC median market rent, 3-bedroom | PENDING — as above | 2025-10 | L | CMHC | PENDING
Rents (affordable / CMHC) | aff_share | 30% | % of homes | Affordable share of homes (per type) | Common Ground locked default | 2026-07 | H | Ubuntu
Rents (affordable / CMHC) | aff_factor | 80% | % of MMR | Affordable rent as % of CMHC MMR | Common Ground locked default | 2026-07 | H | Ubuntu
Operating
Operating | rent_growth | 3% | %/yr | Market rent growth | Common Ground locked default | 2026-07 | M | Ubuntu
Operating | opex_growth | 2.5% | %/yr | Operating expense growth | Common Ground locked default | 2026-07 | M | Ubuntu
Operating | stab_occ | 97% | % | Stabilized physical occupancy (vacancy 3%) | Common Ground locked default (3% vacancy) | 2026-07 | M | Ubuntu
Operating | bad_debt | 0.5% | % of rent | Bad debt / concessions | Analyst placeholder | 2026-09 | L | Analyst | PLACEHOLDER
Operating | opex_util | 1200 | $/occupied home/yr | Utilities (variable) | Common Ground generator default | 2026-07 | M | Ubuntu
Operating | opex_rm | 900 | $/occupied home/yr | Repairs, maintenance, turnover (variable) | Common Ground generator default | 2026-07 | M | Ubuntu
Operating | opex_ins | 450 | $/home/yr | Insurance (fixed on delivered homes) | Common Ground generator default | 2026-07 | M | Ubuntu
Operating | opex_staff | 400 | $/home/yr | On-site staffing (fixed) | Analyst placeholder | 2026-09 | L | Analyst | PLACEHOLDER
Operating | opex_ga | 300 | $/home/yr | Administration (fixed) | Common Ground generator default | 2026-07 | M | Ubuntu
Operating | mgmt_pct | 4% | % of EGI | Property management | Common Ground generator default | 2026-07 | M | Ubuntu
Operating | reserve | 500 | $/home/yr | Replacement reserve (below valuation NOI; deducted for lender DSCR) | Common Ground generator default; treatment per handoff §4 | 2026-07 | M | Ubuntu
Operating | tax_rate | 0.9823% | % of assessed | Multi-residential tax rate, Oshawa 2025 | Arterial (Oshawa 2025). UNVERIFIED — confirm class & current rate | 2025 | L | Arterial | UNVERIFIED
Operating | assess_ratio | 0.6 | × stabilized value | Assessed value as share of stabilized value (new PBR, MPAC lag) | Analyst placeholder; not cost, not price | 2026-09 | L | Analyst | PLACEHOLDER
Operating | cap_rate | 4.25% | % | Valuation cap rate | Common Ground locked default | 2026-07 | M | Ubuntu
Operating | cap_shock | 0% | bps as decimal | Cap-rate stress (+0.01 = +100 bps) | Scenario lever | 2026-09 | H | Analyst
Parking & retail
Parking & retail | pk_m2_space | 32 | m²/space | Below-grade gross area per space | R01 volume allowance (unvalidated layout) | 2026-09 | L | Design | UNVERIFIED
Parking & retail | pk_ratio | 0.65 | spaces/home | Parking ratio (aggregate) | R01; scenario lever | 2026-09 | M | Design
Parking & retail | pk_visitor | 10% | % of spaces | Visitor share (not leased) | Analyst placeholder | 2026-09 | L | Analyst | PLACEHOLDER
Parking & retail | pk_takeup | 60% | % of resident spaces | Resident take-up | Analyst placeholder; no evidence supplied | 2026-09 | L | Analyst | PLACEHOLDER
Parking & retail | pk_rent | 125 | $/space/mo | Parking rent | Analyst placeholder | 2026-09 | L | Analyst | PLACEHOLDER
Parking & retail | ret_eff | 90% | % | Retail rentable efficiency | Analyst placeholder | 2026-09 | L | Analyst | PLACEHOLDER
Parking & retail | ret_rent | 28 | $/sf/yr net | Retail net rent | Analyst placeholder; no retail comps supplied | 2026-09 | L | Analyst | PLACEHOLDER
Parking & retail | ret_vac | 10% | % | Retail vacancy | Analyst placeholder | 2026-09 | L | Analyst | PLACEHOLDER
Parking & retail | ret_ti | 60 | $/sf | Retail TI + inducements | Analyst placeholder | 2026-09 | L | Analyst | PLACEHOLDER
Hard costs
Hard costs | hard_psf | 340 | $/sf above-ground gross | Above-ground construction, up to 12 storeys (midpoint) | Arterial / Altus benchmark $290-390/sf, 'Condos, up to 12 storeys'. Scope, basis and price date NOT inspected | 2026-09 | L | Arterial | UNVERIFIED
Hard costs | hard_shock | 0% | % | Hard-cost stress (±) | Scenario lever | 2026-09 | H | Analyst
Hard costs | pk_psf | 200 | $/sf below-grade gross | Underground parking incl. ramps/systems | Analyst placeholder; assumes benchmark EXCLUDES parking (set 0 if included) | 2026-09 | L | Analyst | PLACEHOLDER
Hard costs | demo_m2 | 75 | $/m² existing footprint | Demolition + hazmat | Analyst placeholder | 2026-09 | L | Analyst | PLACEHOLDER
Hard costs | exist_footprint | 6070 | m² | Existing building footprint (5 buildings) | Arterial site characteristics (2026-07) | 2026-07 | M | Arterial
Hard costs | tenant_term | 500000 | $ | Tenant relocation / lease termination | Analyst placeholder; leases not provided | 2026-09 | L | Analyst | PLACEHOLDER
Hard costs | remed_offsite | 2500000 | $ | Remediation, earthworks, off-site & utility upgrades | Analyst placeholder; no geotech/ESA/servicing study | 2026-09 | L | Analyst | PLACEHOLDER
Hard costs | site_m2 | 150 | $/m² net site | Streets, landscaping, public realm, shared infrastructure | Analyst placeholder | 2026-09 | L | Analyst | PLACEHOLDER
Hard costs | infra_p1_share | 60% | % | Share of site works + remediation paid in Phase 1 (front-loaded) | Handoff §3: Phase 1 carries early shared infrastructure | 2026-09 | M | Analyst
Hard costs | escalation | 3% | %/yr | Escalation from benchmark date (Sept 2026) to phase mid-construction | Analyst placeholder | 2026-09 | L | Analyst | PLACEHOLDER
Hard costs | cont_constr | 7.5% | % of hard | Construction contingency | Analyst placeholder | 2026-09 | M | Analyst
Hard costs | cont_design | 2.5% | % of hard | Design contingency | Analyst placeholder | 2026-09 | M | Analyst
Soft costs & charges
Soft costs & charges | design_pct | 8% | % of hard | Design & consultants | Analyst placeholder | 2026-09 | M | Analyst
Soft costs & charges | permit_pct | 1% | % of hard | Approvals, permits, planning fees | Analyst placeholder | 2026-09 | M | Analyst
Soft costs & charges | dc_per_home | 102653 | $/home | Development charges incl. Region + education (placeholder) | Supplied placeholder $102,653/home; NOT a verified payable rate. City/Region 2025 schedules not reachable from this session | 2026-09 | L | Client | UNVERIFIED
Soft costs & charges | dc_aff_exempt | 0 | 1/0 | Affordable units DC-exempt (DC Act s.4.1)? | Default 0 (conservative). Ontario exempts qualifying affordable rental units since June 2024; eligibility to be confirmed with City/Region | 2026-09 | M | Analyst
Soft costs & charges | dc_credits | 0 | $ | DC credits (existing units / prior payments) | None evidenced | 2026-09 | L | Analyst | PENDING
Soft costs & charges | lease_mkt | 1500 | $/home | Leasing, marketing, pre-opening | Analyst placeholder | 2026-09 | L | Analyst | PLACEHOLDER
Soft costs & charges | dev_fee | 3% | % of hard+soft | Development management fee (Ubuntu / NFP) | Analyst placeholder | 2026-09 | M | Analyst
Soft costs & charges | builders_risk | 0.5% | % of hard | Builder's risk & wrap-up insurance | Analyst placeholder | 2026-09 | M | Analyst
Soft costs & charges | hst_net | 0% | % of hard+soft | Net non-recoverable HST | PENDING tax advice — enhanced GST rental rebate (2023) and Ontario rebate eligibility not confirmed | 2026-09 | L | Tax | PENDING
Capital stack (Common Ground)
Capital stack (Common Ground) | cmhc_share | 50% | % of TDC | CMHC MLI Select insured loan | Common Ground July 2026 (locked) | 2026-07 | H | Ubuntu
Capital stack (Common Ground) | bch_share | 40% | % of TDC | Build Canada Homes tranche | Common Ground July 2026 (locked) | 2026-07 | H | Ubuntu
Capital stack (Common Ground) | city_share | 5% | % of TDC | City contribution | Common Ground July 2026 (locked) | 2026-07 | H | Ubuntu
Capital stack (Common Ground) | grant_share | 54.5% | % of BCH | BCH conditionally-repayable contribution share | Common Ground July 2026 (~54.5%); raise if dscr10 < 1.10 | 2026-07 | M | Ubuntu
Capital stack (Common Ground) | mezz_rate | 4.5% | % | BCH mezz rate (BoC 10-yr + 100 bps), accrues from Year 10 | Common Ground July 2026; BoC bond yield UNVERIFIED | 2026-07 | L | Ubuntu | UNVERIFIED
Capital stack (Common Ground) | mort_rate | 4.25% | % | MLI Select rate (construction + permanent) | Common Ground locked default; lender term sheet NOT obtained | 2026-07 | L | Ubuntu | UNVERIFIED
Capital stack (Common Ground) | rate_shock | 0% | decimal | Borrowing-rate stress (+0.02 = +200 bps) | Scenario lever | 2026-09 | H | Analyst
Capital stack (Common Ground) | amort_yrs | 50 | years | MLI Select amortization | Common Ground locked default | 2026-07 | H | Ubuntu
Capital stack (Common Ground) | cmhc_premium | 2.5% | % of loan | CMHC insurance premium (MLI Select 100-point tier) | Analyst placeholder; confirm premium schedule | 2026-09 | L | Analyst | PLACEHOLDER
Capital stack (Common Ground) | cmhc_app_fee | 200 | $/home | CMHC application fee | CMHC schedule (analyst recollection) | 2026-09 | L | Analyst | PLACEHOLDER
Capital stack (Common Ground) | leaseup_reserve_m | 6 | months of MLI debt service | Lease-up operating / interest reserve capitalized in TDC | Analyst placeholder; lender completion-reserve requirement not obtained | 2026-09 | L | Analyst | PLACEHOLDER
Capital stack (Common Ground) | takeout_ltv | 75% | % | Year-20 takeout refinance LTV (must clear MLI + supplemental + mezz) | Common Ground generator | 2026-07 | M | Ubuntu
Capital stack (Common Ground) | min_dscr | 1.1 | × | Minimum DSCR (MLI Select affordability tier) | CMHC MLI Select | 2026-07 | M | CMHC
Capital stack (Common Ground) | split_lo | 60% | % | Landowner share of net cash flow, Yrs 1-10 (per phase) | Common Ground July 2026 (locked) | 2026-07 | H | Ubuntu
Capital stack (Common Ground) | buyout_prem | 1% | % | Supplemental charge sizing over buyout (fees) | Common Ground generator | 2026-07 | M | Ubuntu
Capital stack (Common Ground) | sell_cost | 2% | % of price | Selling costs (stabilize-and-sell test) | Analyst placeholder | 2026-09 | M | Analyst
Capital stack (Common Ground) | target_yoc | 5.5% | % | Hurdle: unlevered yield on cost (conventional cross-check) | Handoff §7: labelled hurdle, not a house standard | 2026-09 | M | Client
Capital stack (Common Ground) | target_margin | 15% | % | Hurdle: development margin on cost (conventional cross-check) | Handoff §7: labelled hurdle | 2026-09 | M | Client
Capital stack (Common Ground) | disc_rate | 7% | % | Discount rate for dated NPV | Handoff §7: labelled hurdle | 2026-09 | M | Client
Derived (formulas)
| r_m |  |  | Monthly MLI rate
| n_am |  |  | Amortization periods
| cap_eff |  |  | Effective cap rate
| ent_total |  |  | Entitlement months incl. delay
| cap_m |  |  | Effective sitewide leasing capacity, homes/month
| dc_const |  |  | Monthly debt constant (MLI)
| adv_share |  |  | Share of construction window funded by MLI advances
| k_fin |  |  | (placeholder, phase-specific k_fin on Budget)
| sf_per_m2 |  |  | 1 m² = 10.7639104 sf
| horizon |  |  | Model horizon, months (covers Year 20 of the last phase)

## Programme
UBUNTU LAND TRUST & DEVELOPMENTS · Common Ground Initiative
1279 Simcoe Street North — Programme (R01 fixed quantities + suite allocation)
Measured model quantities from Blender masterplan R01 — NOT certified zoning GFA, rentable area or QS areas
Quantity | Unit | Phase 1 | Phase 2 | Phase 3 | Phase 4 | Total | Check / note
Buildings | — | A + B | C | D | E + F
Storeys | st | 8 | 12 | 12 | 12 |  | R01
Homes | homes | 250 | 200 | 200 | 350 |  | R01 — must sum to 1,000 (Checks)
Above-ground area | m² | 21696 | 17568 | 17568 | 29376 |  | R01 modeled floorplate area — 86,208 m²
Residential gross area | m² | 20696 | 16768 | 16768 | 29176 |  | R01 — 83,408 m² (includes circulation/core)
Retail / amenity allowance | m² | 1000 | 800 | 800 | 200 |  | R01 — 2,800 m² (1,000 retail + 1,800 amenity, phase split unverified)
of which retail | m² | 400 | 300 | 300 | 0 |  | ANALYST ALLOCATION of the 1,000 m² retail — verify against design
Parking spaces (R01) | spaces | 175 | 125 | 125 | 225 |  | R01 aggregate 0.65/home; phase ratios differ
Parking spaces (modelled) | spaces
Below-grade area | m² | [5 empty] | spaces × 32 m² — reconciles to R01 20,800 m² (Checks)
Concept FSI (above-ground ÷ net site) | ×
Suite allocation (whole suites, proportional, largest-remainder)
Suite type | Target sf | Phase 1 | Phase 2 | Phase 3 | Phase 4 | Total | R01 target / rounding
Studio | 450 | 25 | 20 | 20 | 35 |  | target 100
1 bedroom | 600 | 125 | 100 | 100 | 175 |  | target 500
2 bedroom | 800 | 80 | 64 | 64 | 112 |  | target 320
3 bedroom | 1000 | 20 | 16 | 16 | 28 |  | target 80
Total homes
Suite rentable area | sf | [5 empty] | R01 681,000 sf (Checks). Suite area / residential gross ≈ 75.85%
Affordable homes (per type, 30%)
Studio affordable
1 bedroom affordable
2 bedroom affordable
3 bedroom affordable
Affordable homes total
Rounding disclosure:
No rounding — proportional allocation produced whole suites.

## Schedule
UBUNTU LAND TRUST & DEVELOPMENTS · Common Ground Initiative
1279 Simcoe Street North — Schedule
No construction dates, durations or lease-up rates have been established (handoff §3) — all schedule inputs are analyst placeholders
Milestone | Unit | Phase 1 | Phase 2 | Phase 3 | Phase 4 | Note
Construction duration | months |  |  |  |  | 8-storey vs 12-storey placeholder durations
Construction start (month #) | month |  |  |  |  | Sequential: next phase starts when previous completes; overlap: fixed interval; later_defer chains through Phases 2-4
Construction complete (month #) | month |  |  |  |  | Occupancy begins the following month
First occupancy (month #) | month
Construction start | date
First occupancy | date
Escalation factor to mid-construction | × |  |  |  |  | Benchmark priced Sept 2026; t_start is 3 months later
Stabilization (month #) | month |  |  |  |  | First month occupancy ≥ homes × stab_occ (sitewide leasing capacity, phase priority)
Stabilization | date
Landowner buyout (month #) | month |  |  |  |  | Year 10 after stabilization
Takeout refinance (month #) | month |  |  |  |  | Year 20: mezz must be cleared
Entitlement (months incl. delay)
All phases stabilized (month #)
Hold end = final stabilization + hold (month #)
Hold end
Model horizon (months)

## Development Budget
UBUNTU LAND TRUST & DEVELOPMENTS · Common Ground Initiative
1279 Simcoe Street North — Development budget (nominal, escalated to each phase's mid-construction)
Benchmark $/sf scope not inspected; parking, site works and contingency added separately (double-count risk noted)
Line | Basis | Phase 1 | Phase 2 | Phase 3 | Phase 4 | Total | Source / note
1. Land & acquisition (Common Ground: lease, not purchase)
Landowner Day-1 draw | draw_pct × appraisal, timed by draw_timing | [5 empty] | 60% of appraisal (Common Ground). Appraisal = seller ask PLACEHOLDER
Land transfer tax | Ontario LTT on draw if ltt_applies | [5 empty] | Off by default — land lease, no transfer
Legal, title, lease registration, due diligence | lump sum, Phase 1 | [5 empty] | PLACEHOLDER
Carrying costs during entitlement | carry_taxes × ent_total/12, Phase 1 | [5 empty] | PLACEHOLDER pending tax bill
2-3. Demolition, remediation, site
Demolition, hazmat, tenant relocation / lease termination | demo_m2 × footprint + tenant_term, Phase 1 | [5 empty] | PLACEHOLDER; leases and hazmat survey not provided
Remediation, earthworks, off-site & utility upgrades | remed_offsite, front-loaded by infra_p1_share | [5 empty] | PLACEHOLDER; no geotech / ESA / servicing study
Streets, landscaping, public realm, shared infrastructure | site_m2 × net site, front-loaded | [5 empty] | Phase 1 carries early shared infrastructure (handoff §3)
4-5. Building construction
Above-ground gross area | m² × 10.7639 | [5 empty] | R01 floorplate area, not QS gross
Below-grade gross area | m² × 10.7639
Above-ground construction (residential, retail shell, amenity) | above_sf × hard_psf × (1+hard_shock) × escalation | [5 empty] | Arterial/Altus $290-390 midpoint — scope UNVERIFIED
Underground parking, ramps, systems | below_sf × pk_psf × escalation | [5 empty] | PLACEHOLDER; set pk_psf = 0 if benchmark includes parking
Hard cost before contingency | sum
Construction + design contingency | (cont_constr + cont_design) × hard base
TOTAL HARD COST
Hard cost per above-ground gross sf | hard ÷ above_sf
7. Development charges & municipal obligations
DC-paying homes | homes less exempt affordable if dc_aff_exempt
Development + education charges (net of credits) | dc_units × dc_per_home − credits (pro rata) | [5 empty] | $102,653/home PLACEHOLDER — not a verified payable rate; payment at construction start
7, 9, 10. Soft costs
Design & consultants | design_pct × hard
Approvals, permits, planning fees | permit_pct × hard
Retail rentable area | retail m² × 10.7639 × ret_eff
Leasing, marketing, pre-opening + retail TI | lease_mkt × homes + ret_ti × retail sf
Builder's risk & wrap-up insurance | builders_risk × hard
Soft costs before fee, HST, reserve | sum incl. legal + carry
Development management fee | dev_fee × (hard + soft_pre + DC)
Net non-recoverable HST | hst_net × (hard + soft_pre) | [5 empty] | PENDING tax advice — 0 until confirmed
Lease-up operating / interest reserve (capitalized) | leaseup_reserve_m × MLI debt service on cost before financing | [5 empty] | Completion-reserve requirement not obtained from lender
TOTAL SOFT COST
11. Financing (closed-form; monthly actuals on Monthly Cash Flow)
Land recognized in cash uses (draw + LTT)
Cash uses before financing | hard + DC + soft + land
MLI advance window | dur × adv_share (months) | [5 empty] | MLI advances start once City + BCH are exhausted
Financing factor k | cmhc_share × (r_m × window/2 + premium)
TOTAL DEVELOPMENT COST (incl. retained land equity) | (base + app fees) ÷ ((1 − land_eq_pct) − k) | [5 empty] | Closed form: TDC = cash uses + capitalized interest + CMHC fees + in-kind land equity
Capitalized MLI construction interest (plan) | TDC × cmhc_share × r_m × window/2 | [5 empty] | Actual monthly interest on Monthly Cash Flow; reconciliation on Checks
CMHC premium + application fees | MLI × premium + homes × fee | [5 empty] | Premium schedule PLACEHOLDER
Landowner retained land equity (in-kind) | land_eq_pct × TDC | [5 empty] | Converts to the Year-10 buyout claim
TDC per home
TDC per gross sf (above + below)
Capital stack (Common Ground July 2026)
CMHC MLI Select (plan) | cmhc_share × TDC
Build Canada Homes tranche | bch_share × TDC
BCH conditionally-repayable contribution | grant_share × BCH | [5 empty] | Vests Yrs 1-10 vs deep affordability; clawback on early sale
BCH mezzanine (BoC+100, payment-free to Yr 10) | BCH − contribution
City contribution | TDC − MLI − BCH − land equity
Stack − TDC (must be 0)
Appraised value donated to affordability | appraisal − Σdraw − Σequity (project level) | [5 empty] | Always shown (Common Ground)

## Revenue & Opex
UBUNTU LAND TRUST & DEVELOPMENTS · Common Ground Initiative
1279 Simcoe Street North — Revenue & operating assumptions (year-1 dollars at stabilization)
Rents are 2024-26 resale listing references (Arterial), not new-build PBR comps; studio rent has NO comp
Item | Basis | Phase 1 | Phase 2 | Phase 3 | Phase 4 | Total | Note
Rent schedule by suite type
Suite | Target sf | Market rent $/mo | $/sf/mo | Comp $/sf/mo | Affordable rent $/mo (80% MMR) | Affordable $/sf | Basis
Studio |  |  |  | n/a |  |  | NO COMP — placeholder
1 bedroom | [6 empty] | Arterial comp at 650 sf; concept suite is smaller so $/sf rises
2 bedroom | [6 empty] | Arterial comp at 1025 sf; concept suite is smaller so $/sf rises
3 bedroom | [6 empty] | Arterial comp at 1300 sf; concept suite is smaller so $/sf rises
Phase revenue (100% occupancy, year-1 $)
Market-rent GPR (annual) | Σ market homes × rent × 12
Affordable-rent GPR (annual) | Σ affordable homes × 80% MMR × 12 | [5 empty] | CMHC MMR values PENDING
Retail net rent (monthly, after vacancy) | retail sf × ret_rent/12 × (1−ret_vac) | [5 empty] | PLACEHOLDER rent; no retail comps
Parking income (monthly, 100% occupancy) | spaces × (1−visitor) × take-up × rent | [5 empty] | PLACEHOLDER take-up and rent; no EV income assumed
Stabilized EGI (annual) | (GPR × occ × (1−bad debt)) + retail + parking × occ
Variable opex (utilities, R&M/turnover) | (util + rm) × homes × occ
Fixed opex (insurance, staffing, admin) | (ins + staff + ga) × homes
Management | mgmt_pct × EGI
NOI before property tax
NOI after property tax (closed form) | NOI_pre ÷ (1 + tax_rate × assess_ratio ÷ cap) | [5 empty] | Assessed value = assess_ratio × stabilized value — NOT cost or price (handoff §4)
Property tax (annual, year-1 $) | tax_rate × assess_ratio × NOI ÷ cap | [5 empty] | 0.9823% multi-residential rate UNVERIFIED
Replacement reserve (annual) | reserve × homes — below valuation NOI; deducted for lender DSCR
Opex ratio (incl. tax) to EGI
NOI per home (year-1 $)

## Debt
UBUNTU LAND TRUST & DEVELOPMENTS · Common Ground Initiative
1279 Simcoe Street North — Debt & funding (Common Ground)
MLI Select construction-to-perm sized on TDC; permanent loan = balance at completion; supplemental charge funds the Year-10 buyout
Item | Basis | Phase 1 | Phase 2 | Phase 3 | Phase 4 | Total | Note
MLI Select (plan, from Budget) | cmhc_share × TDC
MLI permanent loan = construction balance at completion | INDEX(construction balance row, complete) | [5 empty] | Includes actual capitalized interest; construction balance row has no dependency on the permanent payment (no circularity)
Monthly payment | PMT(r_m, n_am, perm)
Annual debt service
Permanent − plan (interest approximation) | [6 empty] | Small; reconciled on Checks (tolerance 2%)
Supplemental charge (Year-10 buyout × (1+prem)) | Σ buyout × (1 + buyout_prem)
Supplemental monthly payment | PMT(r_m, n_am, sup)
City funded | Σ
BCH contribution funded | Σ
BCH mezz funded | Σ
MLI advances incl. capitalized interest | Σ
Capitalized interest (actual) | Σ
Total MLI interest over horizon | Σ construction + permanent
Peak MLI balance | MAX
BCH mezz swept (Yrs 11-20) | Σ
BCH mezz balance at Year 20 | INDEX(balance, stab+240)
Funding order each month: City → BCH contribution → BCH mezz → MLI Select advances (construction interest capitalized). Equity-first vs pari-passu is not a lever under Common Ground because there is no private equity; the landowner's 5% is in-kind.
Permanent debt is NOT sized to DSCR/LTV — Common Ground fixes MLI at 50% of TDC. The DSCR, LTV and debt-yield that result are reported on Phase Returns and tested on Checks; a failing DSCR means the stack does not close at these inputs.

## Monthly Cash Flow
UBUNTU LAND TRUST & DEVELOPMENTS · Common Ground Initiative
1279 Simcoe Street North — Monthly cash flow — phases and consolidated
Month 1 = t_start; 426 months (covers Year 20 of the last phase). Sources = uses monthly; MLI interest capitalized in construction; waterfall per Common Ground
Month # |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 212 | 213 | 214 | 215 | 216 | 217 | 218 | 219 | 220 | 221 | 222 | 223 | 224 | 225 | 226 | 227 | 228 | 229 | 230 | 231 | 232 | 233 | 234 | 235 | 236 | 237 | 238 | 239 | 240 | 241 | 242 | 243 | 244 | 245 | 246 | 247 | 248 | 249 | 250 | 251 | 252 | 253 | 254 | 255 | 256 | 257 | 258 | 259 | 260 | 261 | 262 | 263 | 264 | 265 | 266 | 267 | 268 | 269 | 270 | 271 | 272 | 273 | 274 | 275 | 276 | 277 | 278 | 279 | 280 | 281 | 282 | 283 | 284 | 285 | 286 | 287 | 288 | 289 | 290 | 291 | 292 | 293 | 294 | 295 | 296 | 297 | 298 | 299 | 300 | 301 | 302 | 303 | 304 | 305 | 306 | 307 | 308 | 309 | 310 | 311 | 312 | 313 | 314 | 315 | 316 | 317 | 318 | 319 | 320 | 321 | 322 | 323 | 324 | 325 | 326 | 327 | 328 | 329 | 330 | 331 | 332 | 333 | 334 | 335 | 336 | 337 | 338 | 339 | 340 | 341 | 342 | 343 | 344 | 345 | 346 | 347 | 348 | 349 | 350 | 351 | 352 | 353 | 354 | 355 | 356 | 357 | 358 | 359 | 360 | 361 | 362 | 363 | 364 | 365 | 366 | 367 | 368 | 369 | 370 | 371 | 372 | 373 | 374 | 375 | 376 | 377 | 378 | 379 | 380 | 381 | 382 | 383 | 384 | 385 | 386 | 387 | 388 | 389 | 390 | 391 | 392 | 393 | 394 | 395 | 396 | 397 | 398 | 399 | 400 | 401 | 402 | 403 | 404 | 405 | 406 | 407 | 408 | 409 | 410 | 411 | 412 | 413 | 414 | 415 | 416 | 417 | 418 | 419 | 420 | 421 | 422 | 423 | 424 | 425 | 426
Date
Year #
PHASE 1 — A + B (250 homes) | bar: 1 to 4
Construction flag | P1
Operating flag | P1
Hard cost | P1
Soft cost | P1
Development charges | P1
Landowner draw (+LTT) | P1
CMHC premium & fees | P1
Cash uses before capitalized interest | P1
Cumulative uses, prior month | P1
Cumulative uses | P1
Source: City | P1
Source: BCH contribution | P1
Source: BCH mezz | P1
Source: MLI Select advance (ex interest) | P1
MLI construction interest (capitalized) | P1
MLI construction balance (pre-conversion) | P1
TOTAL USES (incl. capitalized interest) | P1
TOTAL SOURCES | P1
MLI permanent interest | P1
MLI principal | P1
MLI debt service | P1
MLI balance (end of month) | P1
Homes delivered | P1
Homes occupied (sitewide leasing capacity, phase priority) | P1
Net absorption | P1
Stabilized flag | P1
Phase-year since stabilization | P1
Rent growth factor | P1
Opex growth factor | P1
Market rent | P1
Affordable rent | P1
Retail net rent | P1
Parking | P1
Bad debt / concessions | P1
Effective gross income | P1
Variable opex (occupied homes) | P1
Fixed opex (delivered homes) | P1
Management | P1
Property tax | P1
NET OPERATING INCOME | P1
Replacement reserve | P1
Supplemental charge debt service (Yr 10+) | P1
Supplemental charge balance | P1
Net cash flow after debt service | P1
Lease-up reserve draw | P1
Lease-up reserve balance | P1
Landowner Year-10 buyout (equity + MLI paydown) | P1
Landowner cash-flow share (Yrs 1-10) | P1
BCH mezz accrual flag | P1
BCH mezz balance before sweep | P1
BCH mezz sweep (Yrs 11-20, 60% seat) | P1
BCH mezz balance | P1
Non-profit net cash flow | P1
Existing site NOI retained (entitlement only) | P1
Unlevered project cash flow | P1
Check: uses − sources | P1
PHASE 2 — C (200 homes) | bar: 1 to 4
Construction flag | P2
Operating flag | P2
Hard cost | P2
Soft cost | P2
Development charges | P2
Landowner draw (+LTT) | P2
CMHC premium & fees | P2
Cash uses before capitalized interest | P2
Cumulative uses, prior month | P2
Cumulative uses | P2
Source: City | P2
Source: BCH contribution | P2
Source: BCH mezz | P2
Source: MLI Select advance (ex interest) | P2
MLI construction interest (capitalized) | P2
MLI construction balance (pre-conversion) | P2
TOTAL USES (incl. capitalized interest) | P2
TOTAL SOURCES | P2
MLI permanent interest | P2
MLI principal | P2
MLI debt service | P2
MLI balance (end of month) | P2
Homes delivered | P2
Homes occupied (sitewide leasing capacity, phase priority) | P2
Net absorption | P2
Stabilized flag | P2
Phase-year since stabilization | P2
Rent growth factor | P2
Opex growth factor | P2
Market rent | P2
Affordable rent | P2
Retail net rent | P2
Parking | P2
Bad debt / concessions | P2
Effective gross income | P2
Variable opex (occupied homes) | P2
Fixed opex (delivered homes) | P2
Management | P2
Property tax | P2
NET OPERATING INCOME | P2
Replacement reserve | P2
Supplemental charge debt service (Yr 10+) | P2
Supplemental charge balance | P2
Net cash flow after debt service | P2
Lease-up reserve draw | P2
Lease-up reserve balance | P2
Landowner Year-10 buyout (equity + MLI paydown) | P2
Landowner cash-flow share (Yrs 1-10) | P2
BCH mezz accrual flag | P2
BCH mezz balance before sweep | P2
BCH mezz sweep (Yrs 11-20, 60% seat) | P2
BCH mezz balance | P2
Non-profit net cash flow | P2
Existing site NOI retained | P2
Unlevered project cash flow | P2
Check: uses − sources | P2
PHASE 3 — D (200 homes) | bar: 1 to 4
Construction flag | P3
Operating flag | P3
Hard cost | P3
Soft cost | P3
Development charges | P3
Landowner draw (+LTT) | P3
CMHC premium & fees | P3
Cash uses before capitalized interest | P3
Cumulative uses, prior month | P3
Cumulative uses | P3
Source: City | P3
Source: BCH contribution | P3
Source: BCH mezz | P3
Source: MLI Select advance (ex interest) | P3
MLI construction interest (capitalized) | P3
MLI construction balance (pre-conversion) | P3
TOTAL USES (incl. capitalized interest) | P3
TOTAL SOURCES | P3
MLI permanent interest | P3
MLI principal | P3
MLI debt service | P3
MLI balance (end of month) | P3
Homes delivered | P3
Homes occupied (sitewide leasing capacity, phase priority) | P3
Net absorption | P3
Stabilized flag | P3
Phase-year since stabilization | P3
Rent growth factor | P3
Opex growth factor | P3
Market rent | P3
Affordable rent | P3
Retail net rent | P3
Parking | P3
Bad debt / concessions | P3
Effective gross income | P3
Variable opex (occupied homes) | P3
Fixed opex (delivered homes) | P3
Management | P3
Property tax | P3
NET OPERATING INCOME | P3
Replacement reserve | P3
Supplemental charge debt service (Yr 10+) | P3
Supplemental charge balance | P3
Net cash flow after debt service | P3
Lease-up reserve draw | P3
Lease-up reserve balance | P3
Landowner Year-10 buyout (equity + MLI paydown) | P3
Landowner cash-flow share (Yrs 1-10) | P3
BCH mezz accrual flag | P3
BCH mezz balance before sweep | P3
BCH mezz sweep (Yrs 11-20, 60% seat) | P3
BCH mezz balance | P3
Non-profit net cash flow | P3
Existing site NOI retained | P3
Unlevered project cash flow | P3
Check: uses − sources | P3
PHASE 4 — E + F (350 homes) | bar: 1 to 4
Construction flag | P4
Operating flag | P4
Hard cost | P4
Soft cost | P4
Development charges | P4
Landowner draw (+LTT) | P4
CMHC premium & fees | P4
Cash uses before capitalized interest | P4
Cumulative uses, prior month | P4
Cumulative uses | P4
Source: City | P4
Source: BCH contribution | P4
Source: BCH mezz | P4
Source: MLI Select advance (ex interest) | P4
MLI construction interest (capitalized) | P4
MLI construction balance (pre-conversion) | P4
TOTAL USES (incl. capitalized interest) | P4
TOTAL SOURCES | P4
MLI permanent interest | P4
MLI principal | P4
MLI debt service | P4
MLI balance (end of month) | P4
Homes delivered | P4
Homes occupied (sitewide leasing capacity, phase priority) | P4
Net absorption | P4
Stabilized flag | P4
Phase-year since stabilization | P4
Rent growth factor | P4
Opex growth factor | P4
Market rent | P4
Affordable rent | P4
Retail net rent | P4
Parking | P4
Bad debt / concessions | P4
Effective gross income | P4
Variable opex (occupied homes) | P4
Fixed opex (delivered homes) | P4
Management | P4
Property tax | P4
NET OPERATING INCOME | P4
Replacement reserve | P4
Supplemental charge debt service (Yr 10+) | P4
Supplemental charge balance | P4
Net cash flow after debt service | P4
Lease-up reserve draw | P4
Lease-up reserve balance | P4
Landowner Year-10 buyout (equity + MLI paydown) | P4
Landowner cash-flow share (Yrs 1-10) | P4
BCH mezz accrual flag | P4
BCH mezz balance before sweep | P4
BCH mezz sweep (Yrs 11-20, 60% seat) | P4
BCH mezz balance | P4
Non-profit net cash flow | P4
Existing site NOI retained | P4
Unlevered project cash flow | P4
Check: uses − sources | P4
CONSOLIDATED (interphase transfers: none — each phase funds itself; common works paid once in Phase 1) | bar: 1 to 4
Total uses | ALL
City | ALL
BCH contribution | ALL
BCH mezz | ALL
MLI advances (ex interest) | ALL
MLI capitalized interest | ALL
Total sources | ALL
Homes delivered | ALL
Homes occupied | ALL
Effective gross income | ALL
NET OPERATING INCOME | ALL
Replacement reserve | ALL
MLI debt service | ALL
Supplemental debt service | ALL
Net cash flow after debt service | ALL
Landowner share | ALL
Landowner buyout | ALL
BCH mezz sweep | ALL
Non-profit net cash flow | ALL
MLI balance | ALL
BCH mezz balance | ALL
Supplemental balance | ALL
Existing NOI retained | ALL
Unlevered project cash flow | ALL
Check: uses − sources (must be 0) | ALL
Landowner cash received (draw + share + buyout) | ALL
Cumulative public non-repayable + mezz funded | ALL
Unlevered CF incl. terminal value at horizon | ALL
P1 unlevered CF incl. terminal at horizon | P1
P2 unlevered CF incl. terminal at horizon | P2
P3 unlevered CF incl. terminal at horizon | P3
P4 unlevered CF incl. terminal at horizon | P4

## Phase Returns
UBUNTU LAND TRUST & DEVELOPMENTS · Common Ground Initiative
1279 Simcoe Street North — Phase & consolidated returns
Stabilized NOI = 12 months after stabilization; DSCR on lender NOI (after reserve); IRR/NPV dated (XIRR/XNPV)
Metric | Basis | Phase 1 | Phase 2 | Phase 3 | Phase 4 | Consolidated | Note
Programme
Homes
Affordable homes (80% MMR)
Suite rentable area (sf)
Above-ground gross (sf)
Below-ground gross (sf)
Parking spaces
Cost
Total development cost
Cost per home
Cost per gross sf (above + below)
Hard cost per above-ground gross sf
Operations at stabilization
Stabilization month #
Stabilized NOI (12 months after stabilization) | SUMIFS on Monthly Cash Flow
Replacement reserve (same 12 months)
Lender NOI (after reserve)
Stabilized occupancy
Average market rent / home / month (year-1 $)
Average affordable rent / home / month
Unlevered yield on cost (NOI ÷ TDC incl. financing & land equity)
Yield on cost ex financing & land equity | NOI ÷ (TDC − cap. interest − fees − land equity)
Cap rate
Stabilized value (NOI ÷ cap)
Development margin on cost ((value × (1−sell) − TDC) ÷ TDC)
Coverage (Common Ground tests)
DSCR at stabilization (lender NOI ÷ MLI debt service) | [6 empty] | Test 1: ≥ min_dscr
LTV (permanent MLI ÷ value)
Debt yield (lender NOI ÷ permanent MLI)
Year-10 lender NOI (months stab+121..132)
Year-10 debt service (MLI + supplemental)
Year-10 DSCR incl. supplemental | [6 empty] | Test 2: ≥ 1.10 each phase
Minimum non-profit annual cash flow, phase-years 1-20 | MIN of annual SUMIFS by phase-year | [5 empty] | Test 3: ≥ 0
Year-20 value (forward NOI ÷ cap)
Year-20 takeout at takeout_ltv
Year-20 debt to clear (MLI + supplemental + mezz)
Takeout clears all debt? | [6 empty] | Test 4
Who gets what (nominal, over horizon)
Landowner Day-1 draw
Landowner cash-flow share, Yrs 1-10
Landowner Year-10 buyout
Landowner all-in by Year 10 | [6 empty] | Compare with $17M ask (Dashboard)
Landowner retained equity (in-kind)
Non-profit net cash flow (horizon)
BCH mezz recovered (Yrs 11-20)
BCH mezz outstanding at Year 20 (before takeout)
BCH contribution (non-repayable if affordability vests)
City contribution
Exposure & returns
Peak cumulative public funding (City + BCH) | [6 empty] | Consolidated = peak of monthly cumulative; phases never overlap-fund under sequential
Peak MLI balance
Total MLI interest over horizon
Unlevered project IRR (dated, terminal value at horizon) | XIRR
Dated NPV at disc_rate | XNPV
First occupancy
Stabilization
Hold end (final stabilization + hold)

## Exit & Residual
UBUNTU LAND TRUST & DEVELOPMENTS · Common Ground Initiative
1279 Simcoe Street North — Exit tests & residual land value
Common Ground residual = largest appraisal passing all four tests (engine-solved). Conventional residuals shown as labelled cross-checks
A. Stabilize-and-sell test (each phase sold at its stabilization)
Item | Basis | Phase 1 | Phase 2 | Phase 3 | Phase 4 | Total | Note
Sale price at stabilization (NOI ÷ cap)
Selling costs | sell_cost × price
MLI balance discharged at stabilization | INDEX(balance, stab)
BCH mezz discharged
BCH contribution clawback (unvested at sale) | contribution × (1 − years vested/10) | [5 empty] | Sale at stabilization = 0 years vested → 100% clawback
Landowner buyout on sale (retained equity)
Net proceeds to non-profit
Development profit vs TDC (value × (1−sell) − TDC)
Margin on cost
B. Single sale after all phases stabilize (month stab_all)
Forward NOI, 12 months after stab_all
Sale price (NOI ÷ cap)
Selling costs
Debt discharged (MLI + supplemental + mezz at stab_all)
BCH contribution clawback (unvested; Phase 1 partly vested)
Landowner retained equity settled
Net proceeds to non-profit
Development profit vs TDC
Margin on cost
Single sale net proceeds − phased sale net proceeds
Common infrastructure is carried in Phase 1 TDC (infra_p1_share); per-phase profit therefore understates Phase 1 and overstates later phases — the consolidated line is the fair comparison.
C. Hold (Common Ground base case) — position at hold end
Forward NOI at hold end
Value at hold end
Debt at hold end (MLI + supplemental + mezz)
Non-profit equity at hold end
Cumulative non-profit cash flow to hold end
Cumulative landowner cash to hold end
D. Residual land value
Measure | Hurdle / test | Value |  |  |  |  | Note
Common Ground supportable appraisal | All four tests pass (DSCR ≥ min_dscr; DSCR10 ≥ 1.10; NFP ≥ 0; Year-20 takeout) | 0 |  |  |  |  | Engine-solved by bisection on land_appraisal. $0 = fails at any land value
Surplus / (shortfall) vs $17.0M ask |  | -17000000
Break-even above-ground hard cost at $17.0M appraisal | $/sf at which all tests pass | 214.283 |  |  |  |  | vs benchmark $340/sf
Break-even above-ground hard cost at $0 appraisal | $/sf | 221.7111
Break-even starting-rent uplift at benchmark cost | rent_shock at which all tests pass | 38.13% |  |  |  |  | Uniform uplift on market rents
Break-even development charge per home (at $17.0M) | $/home at which all tests pass | n/a |  |  |  |  | 0 or blank = DCs alone cannot fix it
Landowner all-in by Year 10 at $17.0M appraisal (engine) | draw + share + buyout | 79247679.9603 |  |  |  |  | Reconciles to Phase Returns (live)
Conventional cross-checks (live formulas, labelled hurdles — not a house standard)
Cost excluding land recognition (TDC − draw − LTT − land equity)
Land supported at target_yoc (NOI ÷ target_yoc − cost ex land)
Land supported at target_margin (value × (1−sell) ÷ (1+margin) − cost ex land)
Binding conventional residual
Simple value-minus-cost residual (value × (1−sell) − cost ex land − target_margin × TDC)
Landowner all-in by Year 10 − $17.0M ask (live)
Appraised value donated to affordability
E. Approved 172-townhouse plan — for-sale cross-check (what the $17M ask rests on)
Inputs below are placeholders: resale comps are 50-year-old stock at ~$410/sf (Arterial, 8 listings, Centennial, Jun-Jul 2026); Katanna's new-build pricing is VIP-only. Hard cost $250/sf (Arterial, 3-storey stacked townhouse $230-270). DC per townhouse and soft/finance ratios are analyst placeholders.
Units (draft plan; marketing now says 165) |  | 172
Average sellable sf per unit |  | 1300
Sale price $/sf (new build) |  | 550
Gross floor area, sf (supplied 313,966) |  | 313966
Hard cost $/sf GFA (Arterial 3-storey stacked, midpoint) |  | 250
DC + education per townhouse (placeholder) |  | 65000
Soft costs % of hard |  | 18%
Financing & carry % of hard+soft |  | 7%
Selling costs % of revenue |  | 4%
Developer margin % of revenue (hurdle) |  | 15%
Revenue
Costs ex land
Residual land value (revenue × (1 − sell − margin) − costs)
at $500/sf
at $450/sf
at $600/sf

## Sensitivities
UBUNTU LAND TRUST & DEVELOPMENTS · Common Ground Initiative
1279 Simcoe Street North — Sensitivities & stress cases
ENGINE-COMPUTED VALUES (lilac). Analyst stress instructions per handoff §6, not forecasts. Re-run build_workbook.py after changing Inputs. Base row reconciles to live formulas (Checks)
Scenario | Homes | TDC | TDC/home | Stab. NOI | YoC | DSCR | Min DSCR10 | NFP min yr | Takeout | Landowner all-in | BCH mezz @Y20 | Peak public | Stab month | Unlev IRR | PASS?
Single-variable and combined stress (R01 1,000 homes)
Reference case | 1000 | 743389371.8081 | 743389.3718 | 15209224.9629 | 2.046% | 0.8133 | 0.89279 | -1515415.0428 | FAIL | 79247679.9603 | 195502368.1041 | 334525217.3136 | 148 | 3.098% | FAIL
Rents −10% | 1000 | 743389371.8081 | 743389.3718 | 13850460.2199 | 1.863% | 0.73811 | 0.80988 | -1996810.448 | FAIL | 77521840.1167 | 204778986.8565 | 334525217.3136 | 148 | 2.661% | FAIL
Rents +10% | 1000 | 743389371.8081 | 743389.3718 | 16567989.7058 | 2.229% | 0.88848 | 0.97569 | -1034019.6376 | FAIL | 83660710.8895 | 182260908.0646 | 334525217.3136 | 148 | 3.505% | FAIL
Hard cost +15% | 1000 | 822539611.4308 | 822539.6114 | 15209224.9629 | 1.849% | 0.73548 | 0.80562 | -2233019.6496 | FAIL | 84656212.8744 | 226967721.5184 | 370142825.1439 | 148 | 2.629% | FAIL
Hard cost −10% | 1000 | 690622545.3929 | 690622.5454 | 15209224.9629 | 2.202% | 0.875 | 0.96219 | -1037016.7866 | FAIL | 77548183.0153 | 171502422.8461 | 310780145.4268 | 148 | 3.443% | FAIL
Cap rate +100 bps | 1000 | 743389371.8081 | 743389.3718 | 15568319.2512 | 2.094% | 0.83317 | 0.91314 | -1390510.4284 | FAIL | 80123381.903 | 192558096.1522 | 334525217.3136 | 148 | 2.75% | FAIL
Cap rate −50 bps | 1000 | 743389371.8081 | 743389.3718 | 14967613.4878 | 2.013% | 0.79993 | 0.87909 | -1599455.3328 | FAIL | 78772995.7064 | 197353971.0486 | 334525217.3136 | 148 | 3.311% | FAIL
Borrowing +200 bps | 1000 | 751829501.2997 | 751829.5013 | 15209224.9629 | 2.023% | 0.59219 | 0.67069 | -3994085.474 | FAIL | 64884911.6642 | 212467718.9987 | 338323275.5849 | 148 | 3.039% | FAIL
Borrowing −100 bps | 1000 | 739356145.5241 | 739356.1455 | 15209224.9629 | 2.057% | 0.97667 | 1.0498 | -405038.5792 | FAIL | 98188187.6773 | 173130727.8057 | 332710265.4859 | 148 | 3.127% | FAIL
Approvals +12 months | 1000 | 761598791.1255 | 761598.7911 | 15209224.9629 | 1.997% | 0.79397 | 0.87122 | -1679628.1385 | FAIL | 80228397.0391 | 203260859.4944 | 342719456.0065 | 160 | 2.985% | FAIL
Approvals +24 months | 1000 | 780350435.117 | 780350.4351 | 15209224.9629 | 1.949% | 0.775 | 0.85006 | -1848767.6271 | FAIL | 81453647.6114 | 210910364.5033 | 351157695.8026 | 172 | 2.872% | FAIL
Leasing pace −50% | 1000 | 743389371.8081 | 743389.3718 | 15635695.5307 | 2.103% | 0.83627 | 0.91743 | -1323494.9703 | FAIL | 83386072.4803 | 192686693.377 | 334525217.3136 | 162 | 3.333% | FAIL
Leasing pace +25% | 1000 | 743389371.8081 | 743389.3718 | 15132259.0826 | 2.036% | 0.80915 | 0.88753 | -1555757.1959 | FAIL | 78541018.7389 | 195972885.3931 | 334525217.3136 | 145 | 3.044% | FAIL
Parking 0.85/home | 1000 | 766652811.877 | 766652.8119 | 15345292.9839 | 2.002% | 0.79607 | 0.87199 | -1689101.9748 | FAIL | 80810333.2972 | 204257561.6006 | 344993765.3447 | 148 | 2.997% | FAIL
Parking 1.00/home | 1000 | 783944092.7063 | 783944.0927 | 15447350.492 | 1.97% | 0.78397 | 0.85799 | -1812824.173 | FAIL | 82054023.1137 | 210602806.0218 | 352774841.7178 | 148 | 2.924% | FAIL
Parking 0.50/home | 1000 | 726264934.3139 | 726264.9343 | 15107147.3302 | 2.08% | 0.82657 | 0.90786 | -1396451.3908 | FAIL | 78259425.3763 | 188854713.1113 | 326819220.4413 | 148 | 3.175% | FAIL
Existing NOI retained during entitlement | 1000 | 743389371.8081 | 743389.3718 | 15209224.9629 | 2.046% | 0.8133 | 0.89279 | -1515415.0428 | FAIL | 79247679.9603 | 195502368.1041 | 334525217.3136 | 148 | 3.104% | FAIL
Phases 2-4 deferred 12 months | 1000 | 757402960.5866 | 757402.9606 | 15209224.9629 | 2.008% | 0.79834 | 0.87122 | -1679628.1385 | FAIL | 80142388.6714 | 201256891.3721 | 340831332.264 | 160 | 3.048% | FAIL
Overlapping phases (12-mo interval) | 1000 | 703755162.9698 | 703755.163 | 15209224.9629 | 2.161% | 0.85879 | 0.98401 | -881239.9894 | FAIL | 77433028.3259 | 178122904.0442 | 316689823.3364 | 98 | 3.127% | FAIL
Affordable units DC-exempt | 1000 | 708624042.3694 | 708624.0424 | 15209224.9629 | 2.146% | 0.85444 | 0.93526 | -1213302.2477 | FAIL | 78031139.6238 | 179631617.177 | 318880819.0662 | 148 | 3.337% | FAIL
Combined downside | 1000 | 843123537.9369 | 843123.5379 | 14574215.019 | 1.729% | 0.68606 | 0.74917 | -2608666.8028 | FAIL | 89828134.4098 | 236715409.2282 | 379405592.0716 | 174 | 2.101% | FAIL
Density / residual comparison (600/800 are analyst re-builds, 400 is a sensitivity — not designs or verified zoning yields)
Programme | Homes | TDC | TDC/home | Stab. NOI | YoC | DSCR | CG residual appraisal | Conv. residual (binding hurdle) | Note
R01 1,000 homes (modelled) | 1000 | 743389371.8081 | 743389.3718 | 15209224.9629 | 2.046% | 0.8133 | 0 | -418221198.1776 | Blender masterplan R01 — capacity concept
800 homes (analyst re-build) | 800 | 585227841.8703 | 731534.8023 | 12127303.986 | 2.072% | 0.8236 | 0 | -324214360.85 | 800 homes: 4 phases, 8-10 storeys; hard $/sf −3% (analyst)
600 homes (analyst re-build) | 600 | 420294659.5359 | 700491.0992 | 9147775.3604 | 2.177% | 0.86521 | 0 | -221942453.1782 | 600 homes: 3 phases, 6-8 storeys; hard $/sf −7% (analyst, wood/hybrid)
400 homes (analyst re-build) | 400 | 279643199.5611 | 699107.9989 | 6168666.794 | 2.206% | 0.8768 | 0 | -142675770.083 | 400 homes: 2 phases, 6 storeys; sensitivity only — NOT a confirmed as-of-right yield
Consolidated DSCR at stabilization — rent shock (rows) vs hard-cost shock (columns)
rent ↓ / hard cost → | -10% | 0% | 15%
-10% | 0.79412 | 0.73811 | 0.66749
0% | 0.875 | 0.8133 | 0.73548
10% | 0.95589 | 0.88848 | 0.80347
Consolidated stabilized value — rent shock (rows) vs cap-rate shock (columns)
rent ↓ / cap shock → | -0.5% | 0% | 1%
-10% | 363478764.3629 | 325893181.6449 | 270046557.4524
0% | 399136359.6739 | 357864116.7732 | 296539414.3088
10% | 434793954.985 | 389835051.9014 | 323032271.1652
Landowner all-in by Year 10 — appraisal (rows) vs approval delay months (columns)
appraisal ↓ / delay → | 0 | 12 | 24
10000000 | 74838208.2118 | 75768424.2241 | 76952596.5599
17000000 | 79247679.9603 | 80228397.0391 | 81453647.6114
25000000 | 84311382.4496 | 85344885.0434 | 86603603.1967
Consolidated DSCR — appraisal (rows) vs approval delay (columns)
appraisal ↓ / delay → | 0 | 12 | 24
10000000 | 0.81846 | 0.79889 | 0.77969
17000000 | 0.8133 | 0.79397 | 0.775
25000000 | 0.80747 | 0.78842 | 0.76972
Consolidated YoC — hard $/sf (columns: $290 / $340 / $390 benchmark range)
rent ↓ / hard $/sf → | 290 | 340 | 390
0% | 2.284% | 2.046% | 1.853%

## Dashboard
UBUNTU LAND TRUST & DEVELOPMENTS · Common Ground Initiative
1279 Simcoe Street North — Investment dashboard — Common Ground, R01 1,000 homes
Live formulas; scenario summary on Sensitivities
PROGRAMME
Homes / affordable homes
Suite rentable area (sf)
Above / below-ground gross (sf)
Parking spaces
COST
Total development cost
Cost per home
Hard cost per above-ground gross sf
Development charges
Land recognized (draw + retained equity) / donated
OPERATIONS
Stabilized NOI (consolidated)
NOI per home
Unlevered yield on cost
Cap rate / stabilized value
Development margin on cost
COVERAGE — COMMON GROUND TESTS
DSCR at stabilization (test ≥ min_dscr)
Minimum phase Year-10 DSCR (test ≥ 1.10)
Minimum non-profit annual cash flow (test ≥ 0)
Year-20 takeout clears debt (test)
ALL TESTS PASS?
LTV / debt yield on permanent MLI
LAND
Appraisal tested (seller ask, placeholder)
Common Ground supportable appraisal (engine) | 0
Surplus / (shortfall) vs ask (engine) | -17000000
Landowner all-in by Year 10 (draw + share + buyout)
Landowner all-in − ask
Conventional residual at labelled hurdles (binding)
Break-even hard $/sf at ask (engine) | 214.283
Break-even rent uplift at benchmark cost (engine) | 38.13%
EXPOSURE
Peak cumulative public funding (City + BCH)
Peak MLI balance
Total MLI interest over horizon
BCH mezz outstanding at Year 20 (before takeout)
Unlevered project IRR / dated NPV
DATES
Financial close (t_start)
Phase 1 construction start
First occupancy (Phase 1)
All phases stabilized
Hold end
Phase summary (live)
Phase | Homes | TDC | TDC/home | Stab. NOI | YoC | DSCR | DSCR10 | Value | Landowner all-in | Stabilization

## Checks
UBUNTU LAND TRUST & DEVELOPMENTS · Common Ground Initiative
1279 Simcoe Street North — Model checks
All must read TRUE
Check | Result | Detail
Phase homes sum to 1,000
Suite types sum to 1,000
Suite area sums to 681,000 sf
Above-ground area sums to 86,208 m²
Residential gross sums to 83,408 m²
Other allowances sum to 2,800 m²
Parking sums to 650 spaces at R01 ratio
Below-grade sums to 20,800 m² at R01 ratio
Sources = uses every month (all phases)
Capital stack = TDC each phase
Permanent MLI within 2% of plan (interest approximation)
MLI balances roll (no negative balance)
Mezz balances roll (no negative balance)
No rent before occupancy
No existing income after entitlement
Each phase stabilizes within horizon
Year 20 of last phase within horizon
Common works counted once (Phase 1 shares sum to 1)
Non-profit never carries an unfunded lease-up deficit beyond reserve |  | min reserve balance
Landowner buyout occurs exactly once per phase
Scenario levers at baseline (rent/hard/cap/rate shocks = 0, delay = 0, pace = 1) |  | Reset these to reproduce the engine base case
Engine base case reconciles: TDC within 0.1% |  | engine TDC 743,389,372
Engine base case reconciles: stabilized NOI within 0.5% |  | engine NOI 15,209,225
Engine base case reconciles: DSCR within 0.01x |  | engine DSCR 0.813
Engine base case reconciles: landowner all-in within 1% |  | engine 79,247,680
Common Ground tests: DSCR ≥ min_dscr
Common Ground tests: every phase DSCR10 ≥ 1.10
Common Ground tests: non-profit annual CF ≥ 0
Common Ground tests: Year-20 takeout clears debt
ALL MODEL-INTEGRITY CHECKS PASS (rows 6-25)
COMMON GROUND FEASIBILITY (last four rows) — expected FAIL at benchmark inputs